## Implementation Checklist
No. | Responsible AI Principle | Implementation Requirement | Implementation Activity / Action | Required Documentation / Evidence | Responsible Owner | Priority | Implementation Status | Target Date | Remarks
1 | Accountability | Assign an Individual Owner for each AI system. | Record the designated owner in the AI inventory.
2 | Accountability | Define responsibilities for business, development, data, security, privacy and compliance teams. | Create and approve a RACI matrix.
3 | Accountability | Establish an AI Governance Committee or equivalent oversight mechanism. | Define committee membership, authority, responsibilities and meeting frequency.
4 | Accountability | Establish an AI governance escalation process. | Document escalation criteria, routes and response responsibilities.
5 | Accountability | Assign owners to AI risks and remediation actions. | Maintain an AI risk register with accountable owners and target dates.
6 | Fairness and Non-Discrimination | Assess AI systems for potential bias and discriminatory outcomes. | Perform a fairness and bias impact assessment before deployment.
7 | Fairness and Non-Discrimination | Test AI outcomes across relevant groups. | Conduct fairness testing and document results.
8 | Fairness and Non-Discrimination | Establish periodic fairness reassessment. | Include periodic fairness monitoring in the post-deployment review process.
9 | Transparency | Document the purpose and intended use of each AI system. | Create and maintain AI system documentation.
10 | Transparency | Inform users when they are interacting with AI where appropriate. | Implement suitable AI disclosure notices.
11 | Transparency | Document AI capabilities and limitations. | Prepare user guidance, system documentation or model cards.
12 | Transparency | Maintain appropriate information about data, models and providers. | Maintain AI inventory and technical documentation.
13 | Transparency | Establish change documentation requirements. | Record material AI system, model, data and configuration changes.
14 | Transparency | Document how AI is used in business processes. | Update process maps and operating procedures.
15 | Explainability | Identify AI decisions requiring meaningful explanations. | Document decision types and explanation requirements.
16 | Explainability | Define how explanations will be provided to affected users where applicable. | Create an explanation process and supporting user interfaces.
17 | Explainability | Ensure explanations are understandable to intended audiences. | Test explanation usability and comprehension.
18 | Explainability | Reassess explainability after significant changes. | Include explainability validation in change management.
19 | Privacy and Data Protection | Conduct a PIA/DPIA where required. | Complete and approve the applicable privacy impact assessment.
20 | Privacy and Data Protection | Establish a lawful basis or appropriate justification for personal-data processing. | Document privacy and legal basis for processing.
21 | Privacy and Data Protection | Define purpose limitation requirements. | Document permitted purposes and prevent unauthorized secondary use.
22 | Privacy and Data Protection | Implement data minimization. | Collect and process only necessary personal data.
23 | Privacy and Data Protection | Protect personal and sensitive data. | Implement appropriate encryption, access control, masking and other safeguards.
24 | Privacy and Data Protection | Define retention and deletion requirements. | Establish retention schedules and secure deletion procedures.
25 | Privacy and Data Protection | Support applicable individual privacy rights. | Document procedures for access, correction, deletion and other applicable rights.
26 | Privacy and Data Protection | Assess third-party AI providers for privacy risks. | Perform vendor privacy due diligence and contract reviews.
27 | Privacy and Data Protection | Protect personal data in prompts, inputs and outputs. | Implement prompt/data handling rules, DLP and access controls.
28 | Security and Resilience | Perform an AI-specific security risk assessment. | Identify threats to models, data, prompts, APIs and infrastructure.
29 | Security and Resilience | Protect AI assets from unauthorized access. | Implement IAM, least privilege and secure administration.
30 | Security and Resilience | Implement authentication and authorization controls. | Apply appropriate access controls to AI systems and interfaces.
31 | Security and Resilience | Protect model and data integrity. | Implement integrity, version control and change controls.
32 | Security and Resilience | Assess AI-specific threats. | Perform threat modeling for poisoning, prompt injection, leakage, manipulation and related threats.
33 | Security and Resilience | Establish vulnerability management. | Scan, assess, prioritize and remediate vulnerabilities.
34 | Security and Resilience | Implement AI security logging and monitoring. | Configure relevant audit logs, monitoring and alerting.
35 | Security and Resilience | Establish backup and recovery capabilities where appropriate. | Document and test backup and recovery procedures.
36 | Security and Resilience | Test resilience. | Conduct appropriate continuity, recovery and resilience tests.
37 | Safety and Reliability | Define performance and reliability requirements. | Establish measurable performance, availability and reliability criteria.
38 | Safety and Reliability | Define accuracy and other relevant performance metrics. | Establish KPIs, thresholds and acceptance criteria.
39 | Safety and Reliability | Identify failure scenarios. | Perform failure-mode and adverse-outcome analysis.
40 | Safety and Reliability | Implement safeguards for harmful outcomes. | Deploy technical and procedural safety controls.
41 | Safety and Reliability | Establish handling procedures for erroneous or unsafe outputs. | Create incident and exception handling procedures.
42 | Safety and Reliability | Monitor performance after deployment. | Implement production performance monitoring.
43 | Human Oversight | Define human oversight requirements based on risk. | Document required level and type of human oversight.
44 | Human Oversight | Identify mandatory human intervention points. | Embed review and approval points in business processes.
45 | Human Oversight | Enable authorized override or shutdown where necessary. | Implement override, intervention or stop mechanisms.
46 | Human Oversight | Train personnel responsible for AI oversight. | Provide role-specific AI, risk and system training.
47 | Human Oversight | Define when human review is required. | Document review triggers and escalation criteria.
48 | Human Oversight | Maintain evidence of human review. | Implement appropriate review records and audit trails.
49 | Human Oversight | Provide reviewers sufficient information for informed decisions. | Design interfaces and procedures that support meaningful review.
50 | Risk-Based Approach | Classify AI systems according to risk and intended use. | Establish and apply an AI risk classification methodology.
51 | Risk-Based Approach | Perform an AI risk assessment before deployment. | Document risks, impacts, likelihood and controls.
52 | Risk-Based Approach | Apply enhanced governance to high-risk systems. | Define additional testing, approval, documentation and monitoring requirements.
53 | Risk-Based Approach | Document and approve residual risks. | Establish risk acceptance authority and records.
54 | Risk-Based Approach | Reassess risk after significant changes. | Integrate risk reassessment into change management.
55 | Ethical and Responsible Use | Define intended and prohibited AI use. | Establish acceptable-use and prohibited-use requirements.
56 | Ethical and Responsible Use | Restrict harmful, inappropriate or unauthorized uses. | Implement policy and technical restrictions.
57 | Ethical and Responsible Use | Provide responsible AI guidance and training. | Deliver employee awareness and role-specific training.
58 | Continuous Monitoring and Improvement | Establish ongoing AI monitoring. | Define monitoring scope, frequency, responsibilities and escalation.
59 | Continuous Monitoring and Improvement | Monitor performance, fairness, security and risk indicators. | Implement relevant KPIs/KRIs and reporting.
60 | Continuous Monitoring and Improvement | Monitor model/data drift where applicable. | Define drift metrics, thresholds and response actions.
61 | Continuous Monitoring and Improvement | Analyze incidents, complaints and errors. | Establish root-cause analysis and trend reporting.
62 | Continuous Monitoring and Improvement | Report monitoring results to governance bodies. | Define management and committee reporting requirements.
63 | Continuous Monitoring and Improvement | Track corrective actions. | Maintain an action tracker through closure.
64 | Compliance with Laws and Standards | Identify applicable laws, regulations and standards. | Maintain an AI legal, regulatory and standards register.
65 | Compliance with Laws and Standards | Incorporate regulatory and contractual requirements into AI requirements. | Update system requirements, contracts and controls.
66 | Compliance with Laws and Standards | Perform periodic AI compliance assessments. | Establish compliance review frequency and methodology.
67 | Compliance with Laws and Standards | Monitor regulatory changes. | Assign responsibility for regulatory horizon scanning.
68 | Compliance with Laws and Standards | Track and remediate compliance gaps. | Maintain compliance findings and corrective action plans.

## Implementation Summary
Responsible AI Principle | Total Requirements | Implemented | Partially Implemented | In Progress | Not Started | Not Applicable
Accountability | 5 | 0 | 0 | 0 | 0 | 0
Fairness and Non-Discrimination | 3 | 0 | 0 | 0 | 0 | 0
Transparency | 6 | 0 | 0 | 0 | 0 | 0
Explainability | 4 | 0 | 0 | 0 | 0 | 0
Privacy and Data Protection | 9 | 0 | 0 | 0 | 0 | 0
Security and Resilience | 9 | 0 | 0 | 0 | 0 | 0
Safety and Reliability | 6 | 0 | 0 | 0 | 0 | 0
Human Oversight | 7 | 0 | 0 | 0 | 0 | 0
Risk-Based Approach | 5 | 0 | 0 | 0 | 0 | 0
Ethical and Responsible Use | 3 | 0 | 0 | 0 | 0 | 0
Continuous Monitoring and Improvement | 6 | 0 | 0 | 0 | 0 | 0
Compliance with Laws and Standards | 5 | 0 | 0 | 0 | 0 | 0

## Overall Status
Metric | Value
Total Implementation Requirements | 68
Implemented | 0
Partially Implemented | 0
In Progress | 0
Not Started | 0
Not Applicable | 0
High Priority Items | 0
Medium Priority Items | 0
Low Priority Items | 0